## Project Plan
Daily tasks may include high level goals and details.
| 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7
Day | 2015-08-11 | 2015-08-12 | 2015-08-13 | 2015-08-14 | 2015-08-15 | 2015-08-16 | 2015-08-17 | 2015-08-18 | 2015-08-19 | 2015-08-20 | 2015-08-21 | 2015-08-22 | 2015-08-23 | 2015-08-24 | 2015-08-25 | 2015-08-26 | 2015-08-27 | 2015-08-28 | 2015-08-29 | 2015-08-30 | 2015-08-31
Tasks | * Thoroughly study GraphChi preprocessing code & resolve all issues * Go through GraphChi Sections 2, 3, 4, * Correlate (2,3,4) above with code * Review Kai's system design with Zhiqiang | * Create BitBucket Repository * Correlation of all sections with code is now unnecessary - only focus on prepro- cessing. * Write basic structure of code. * Identify reusable components from graphchi. | * Create a preprocessing plan. |  |  |  |  | *Need to Understand all files generated in preprocessing |  | * To finish Preprocessing
| 8 |  |  | 9 |  |  | 10 |  |  | 11 |  |  | 12 |  |  | 13 |  |  | 14 |  |  | 15 |  |  | 16 |  |  | 17
Day | 2015-09-01 | 2015-09-02 | 2015-09-03 | 2015-09-04 | 2015-09-05 | 2015-09-06 | 2015-09-07 | 2015-09-08 | 2015-09-09 | 2015-09-10 | 2015-09-11 | 2015-09-12 | 2015-09-13 | 2015-09-14 | 2015-09-15 | 2015-09-16 | 2015-09-17 | 2015-09-18 | 2015-09-19 | 2015-09-20 | 2015-09-21 | 2015-09-22 | 2015-09-23 | 2015-09-24 | 2015-09-25 | 2015-09-26 | 2015-09-27 | 2015-09-28 | 2015-09-29 | 2015-09-30
Tasks
| 18 |  |  | 19 |  |  | 20 |  |  | 21 |  |  | 22 |  |  | 23 |  |  | 24 |  |  | 25 |  |  | 26 |  |  | 27 |  |  | 28
Day | 2015-10-01 | 2015-10-02 | 2015-10-03 | 2015-10-04 | 2015-10-05 | 2015-10-06 | 2015-10-07 | 2015-10-08 | 2015-10-09 | 2015-10-10 | 2015-10-11 | 2015-10-12 | 2015-10-13 | 2015-10-14 | 2015-10-15 | 2015-10-16 | 2015-10-17 | 2015-10-18 | 2015-10-19 | 2015-10-20 | 2015-10-21 | 2015-10-22 | 2015-10-23 | 2015-10-24 | 2015-10-25 | 2015-10-26 | 2015-10-27 | 2015-10-28 | 2015-10-29 | 2015-10-30 | 2015-10-31
Tasks | * To get system Ready
| 29 |  | 30 |  |  | 31 |  |  | 32 |  |  | 33 |  |  | 34 |  |  | 35 |  |  | 36 |  |  | 37 |  |  | 38 |  |  | 39
Day | 2015-11-01 | 2015-11-02 | 2015-11-03 | 2015-11-04 | 2015-11-05 | 2015-11-06 | 2015-11-07 | 2015-11-08 | 2015-11-09 | 2015-11-10 | 2015-11-11 | 2015-11-12 | 2015-11-13 | 2015-11-14 | 2015-11-15 | 2015-11-16 | 2015-11-17 | 2015-11-18 | 2015-11-19 | 2015-11-20 | 2015-11-21 | 2015-11-22 | 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26 | 2015-11-27 | 2015-11-28 | 2015-11-29 | 2015-11-30
Tasks
|  |  | 40 |  |  | 41
Day | 2015-12-01 | 2015-12-02 | 2015-12-03 | 2015-12-04 | 2015-12-05 | 2015-12-06 | 2015-12-07 | 2015-12-08
Tasks

## Project Components
| ID | Project Components | Notes
1 | 1 | Implementation
2 | 2 | Evaluation
3 |  | Generation of Input Graph
4 |  | Selection of Evaluation Criteria
5 | 3 | Literature Review
6 | 4

## Resources and GraphChi Info
!!! - Issue¦>>> - Resolution¦@@@ - Innovative Idea¦* - Note
| ID | Resources | Notes
1 | 1 | Paper GraphChi
2 |  | 2 Disk-based Graph Computation
3 |  | 2.1 Computational Model
4 |  | 2.2 Standard Sparse Graph Formats | !!! See problems below
5 |  | 2.3 Random Access Problem
6 |  | 3 Parallel SlidingWindows
7 |  | 3.1 Loading the Graph
8 |  | 3.2 Parallel Updates
9 |  | 3.3 Updating Graph to Disk
10 |  | 3.4 Example
11 |  | 3.5 Evolving Graphs
12 |  | 3.6 Analysis of the I/O Costs
13 |  | 3.7 Remarks
14 |  | 4 System Design & Implementation
15 |  | 4.1 Shard Data Format
16 |  | 4.2 Main Execution
17 |  | 4.3 Selective Scheduling
18 |  | 5 Programming Model
19 | 2 | Paper GraphLab | designing and implementing efficient and provably correct parallel algorithms is extremely challenging.
20 | 3 | GraphChi Implementation | Refer to GraphChiImplementationStudy.xlsx
21 | 4 | GraphChi Github Material
22 | 5 | Live Journal Input Graph | http://snap.stanford.edu/data/soc-LiveJournal1.html https://github.com/GraphChi/graphchiDB-scala
23 | 6 | Netflix Input Graph | http://www.select.cs.cmu.edu/code/graphlab/datasets/ https://github.com/GraphChi/graphchiDB-scala
| ID | GraphChi Concepts/Details | Type | Notes
| 1 | asynchronous model of computation | concept level
| 2 | prefix sum | concept/implementational | 8/11/2015 * paper by blelloch !!! What is its exact benefit in graphchi?
| 3 | Bulk Synchronous parallel model | concept level | * update functions can only observe values from the previous iterations
| 4 | CSR/CSC | concept/implementational | 8/11/2015 !!! Need to better understand the disadvantage of CSR. !!! How is CSC solving the problem? !!! What is a transposed graph? See Section 2.2 in Graphchi paper for above.

## GraphChi Implementation Notes
!!! - Issue¦>>> - Resolution¦@@@ - Innovative Idea¦* - Note
| ID | Packages | Category | Notes | Imp Methods
1 | 1 | graphchi.preprocessing | Important
2 |  | Interface:EdgeProcessor.java
3 |  | Interface:VertexProcessor.java
4 |  | FastSharder.java |  | *it is assumed that probablistically the number of edges is roughly even *they do some kind of memory optimization based on degrees. 8/11/2015 !!! What is the difference between shovelStreams and vertexShovelStreams? >>> vertexShovelStreams will have vertex values, we don't need them. !!! What is the significance of using SparseDegrees technique? !!! Understand the difference between the 2 usages, Lines 34-43 >>> These are just two types of usages easy. !!! Do we need edge processor, vertex processor lines 79-80? !!! What is a degree vertex? Line 260 !!! What is a sparse representation? Line 304 !!! Why do we need to keep track of vertex degrees in-memory? Line 806 * I don't think we need computeVertexDegrees() | FastSharder(String, int, VertexProcessor<VertexValueType>, EdgeProcessor<EdgeValueType>, BytesToValueConverter<VertexValueType>, BytesToValueConverter<EdgeValueType>) shovelFilename(int) vertexShovelFileName(int) addEdge(int, int, String) addToShovel(int, int, int, EdgeValueType) isAllowSparseDegreesAndVertexData() setAllowSparseDegreesAndVertexData(boolean) addVertexValue(int, int, VertexValueType) packEdges(int, int) getFirst(long) getSecond(long) process() writeDegrees() writeIntervals() saveVertexTranslate() processVertexValues(boolean) processShovel(int) partition(long[], byte[], int, int, int)
|  |  |  | * We'll need to computevertexdegree() to know beforehand what size of an array we'll need to store the vertices. * We won't need MatrixMarket Format * The shovel generated is not in memory * The shovels are read into the memory before sorting and producing the final shards. * FastSharder() Creates the shovelstreams. !!! Line 162, receiveVertexValue body? >>> A type interface which is overriden by a concrete method. | quickSort(long[], byte[], int, int, int) sortWithValues(long[], byte[], int) shard(InputStream, GraphInputFormat) shard(InputStream, String) shard(InputStream) computeVertexDegrees() main(String[])
8/12/2015 * packing is done to unify 2 vertices into one object
5 |  | VertexIdTranslate.java |  | *translates the vertex ids. The trick enables the distribu- tion of vertices into shards s.t they are evenly distributed. This obviates the need to count all the vertices in the graph and divide the vertices.
6 | 2 | graphchi
7 |  | ChiLogger.java |  | *for logging processing steps in the console. *skimmed
8 |  | ChiVertex.java
9 |  | ChiFilenames.java
10 |  | EmptyType.java
11 |  | GraphChiContext.java
12 |  | Enum:EdgeDirection.java
13 |  | Interface:ChiEdge.java |  | *Edge interface representing edge data
14 |  | Interface:Scheduler.java
15 |  | Interface:GraphChiProgram.java
16 | 3 | graphchi.engine | Important
17 | 4 | graphchi.engine.auxdata | Important
18 | 5 | graphchi.datablocks | Important
19 |  | Interface:BytesToValueConverter.java
20 |  | FloatConverter.java
21 |  | FloatPairConverter.java
22 |  | IntConverter.java
23 |  | LongConverter.java
24 | 6 | graphchi.io
25 | 7 | graphchi.shards | Important
26 | 8 | graphchi.queries | Later | 8/16/2015 8:29 PM Don't need this for preprocessing
27 | 9 | graphchi.queries.demo | Later | 8/16/2015 8:29 PM Don't need this for preprocessing
8/17/2015 2:38 PM !!! Need to look into friendsoffriends.java. Seems useful for DTC
28 | 10 | graphchi.util
29 | 11 | graphchi.apps
|  | Pagerank.java |  | 8/12/2015 * Like most apps run on GraphChi it has 3 components: creating the shards, running graphchi engine, and outputting the results. * For now concentrating only on the create shards part. * Understood create shards part
8/19/2015 1:52 PM What is the meaning of piping in graph?
30 | 12 | graphchi.apps.kcore
31 |  | GraphTransformer.java
32 | 13 | graphchi.apps.util
33 | 14 | nom.tam.util

## Issues
These issues may include questions that arise during discussions, from reading other resources, or coding. These issues may or may not be mentioned elsewhere. The striked out issues are dealt with, the ones in green are the ones that need to mentioned in the paper, the ones in yellow are the ones that don't need to be mentioned in the paper.
ID | Implementation Issue | Date Entered | Notes | Date Cleared
1 | How to account for duplicate edges? | 2015-08-10 19:03 | accounted
2 | How to store edges in the disk? | 2015-08-10 19:03 | *possible solution is to use an edge list, which is memory inefficient, and an adjacency list.
3 | How to store edges in the memory? | 2015-08-10 19:04 | done
4 | How to perform computations of the percentages efficiently? | 2015-08-10 19:04
5 | We'll need to calculate degree vertices. | 2015-08-11 23:13 | done
6 |  | 2015-08-11 23:14 | need to go through graphchi's plan
7 | Need to consider the format of the data in the disk. (Unsorted and adjacency list format.) | 2015-08-13 10:22 | * an adjacency list is space efficient, but it would not be possible to ensure all the edges with the same source are in the same list. This is because we shall be streaming the edges to reader rather than reading them all as a whole.
8 | Generate partitions such that the source vertices of the edges are in the same interval. | 2015-08-13 10:23 | done
9 | Need to consider the format of the edge values | 2015-08-14 11:57 | byte format
10 | What are the intermediate files being generated after the processing of GraphChi? | 2015-08-16 20:38 | * They appeared garbled, I think this is because they were translated into a smaller format.
11 | What is the MatrixMarket Format? The netflix graphs are apparently available in this format. | 2015-08-16 21:49
12 | What is piping in of graph? | 2015-08-16 22:06
13 | Twitter graph contains no edge values | 2015-08-17 23:26 | taken care of | n/a
14 | Skip using VertexValue | 2015-08-18 16:31 | done | n/a
15 | Byte representation is sufficient for edge value | 2015-08-19 16:31 |  | n/a
16 | Loading vertex ids into memory is unnecessary, vertex ids are implicit | 2015-08-19 16:31 |  | n/a
17 | byte arrays are used to store values as binary data in disk | 2015-08-19 16:31 |  | n/a
18 | include offset in partition files so that we don't need to read the entire file when performing computation | 2015-08-20 15:27 | remaining
19 | Store the partition files in the form of adjacency lists, for space compression | 2015-08-20 15:28 | done
20 | Cannot use arrayList for storing vertex degrees | 2015-08-26 21:31 | This is because each element of an arraylist uses 8-12 bytes, that means 12 Gigs req for a graph of a billion vertices . Although this is less of a problem now as we shall not load the degrees of all the vertices, but only of those which are in the partitions loaded in the memory for computation.
21 | Each partition needs to have roughly the same number of edges. | 2015-08-26 21:34 | done
22 | We need to guarantee all edges with the same source are in the same partition. | 2015-08-26 21:34 | done
23 | The situation where the number of edges with the same source vertex is greater than the partition size should be tackled | 2015-08-26 21:36 | This case has been handled., | 2015-08-26 21:37
24 | Corresponding to point 20, we also cannot just use an array, for we'll need to resize the array everytime we add a new element in the list, for which we shall need to copy the entire array, which may lead to outofmemory errors too. | 2015-08-26 21:47 | We actually do use an array. Degree data structure only contains the counts which can be updated. In addition, we also need to initialize a new degrees file as per the sizes of the partitions being processed.
25 | We need to use a byte array for the vertex degrees, we'll run out of memory otherwise. | 2015-08-26 23:21 | Can't, since there is a large number of vertices, we need int for degrees too.
26 | Available Free memory is different for different executions | 2015-09-02 16:43 |  | n/a
27 | clearing a map variable or assigning to null does not free the memory | 2015-09-02 16:44 |  | n/a
28 | Need to set our policy for setting the partition size, especially if one vertex has a very large degree…(kind of like an outlier), in which case if we set partSize to the degree of the vertex with max degree, we'll have many partitions with lots of free space, you end up utilizing too few partitions. | 2015-09-03 00:07 | One possibility is to set partitions of variable sizes. Two, create an outlier partition for
29 | It is difficult to ensure the number of partitions may be fixed, there may be a few more or a few less. | 2015-09-03 02:09 | can be solved by keeping track of a partition space usage - but this strategy seems complicated. - this is an NP hard problem, the bin packing problem. http://stackoverflow.com/questions/16588669/spread-objects-evenly-over-multiple-collections | 2015-09-03
30 | read from middle of a file. | 2015-09-06 19:28 | how to keep track of the newly added edges?
ID | Concept Issue | Date Entered | Notes | Date Cleared

## Project Tool Usage
Note
8/14/2015 1:06 PM !!! How to push exisiting project in Eclipse to an existing repository in bitbucket? * Don’t intend to use maven as of now, as git can do most of what maven does. BUT NEED TO EXPLORE MORE ON THIS Project is now Maven